Project 4 — Privacy Compliance Audit

Organisation: LillyPut Healthcare Ltd

Sector: Domiciliary Healthcare

Audit Type:  Mini Privacy Compliance Audit

Prepared by:  [ Rhoda Agyei Mensah]

Date:  [17th  July 2026]

Status: Portfolio Project — Fictional Organisation

- **Disclaimer:** LillyPut Healthcare Ltd is a fictional organisation created for portfolio purposes. All evidence and findings in this audit are fictional and use synthetic information.

- Audit Objective

The purpose of this mini audit is to assess whether LillyPut Healthcare Ltd has appropriate privacy and information-governance arrangements for protecting personal and sensitive healthcare information.

The audit considers key areas of privacy compliance, including transparency, retention, access control, staff awareness, breach management, DPIAs, data sharing, records management, individual rights and supplier governance.

The audit uses a simplified evidence-based approach:

“Requirement → Evidence → Finding → Risk → Recommendation → Owner → Deadline → Audit Status”

Risk ratings used:

Low— Limited risk; existing controls appear generally appropriate.

Medium — Improvement required to reduce the risk.

High — Significant gap requiring priority action.

2. Mini Privacy Audit Findings

| Requirement | Evidence | Finding | Risk | Recommendation | Owner | Deadline | Audit Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Privacy notice | Website privacy notice reviewed | Some processing activities and retention information are unclear | Medium | Update privacy notice to clearly explain purposes, lawful bases, sharing, retention and individual rights | DPO/IG Lead | 45 days | Open |
| Data retention | Retention schedule | Several healthcare records have no confirmed retention period | Medium | Complete retention schedule and assign review owners | Records Manager | 60 days | Open |
| Access control | System access list and annual review | Annual reviews are evidenced; role-change reviews need strengthening | Low | Continue periodic reviews and introduce reviews following role changes | IT/System Owners | Ongoing | In Progress |
| Staff training | Training report: 82% completion | 18% of relevant staff have not completed current privacy training | Medium | Complete outstanding training and monitor through management reporting | HR/Managers | 30 days | Open |
| Data breach procedure | Breach policy and incident form | Procedure exists but has not been tested recently | Medium | Conduct breach-response tabletop exercise and record lessons learned | IG/IT/Management | 60 days | Open |
| DPIAs | DPIA folder/register | No central DPIA register; assessments are difficult to track | High | Create central DPIA register and formal DPIA screening process | DPO/IG Lead | 30 days | Open — High Priority |
| Data sharing | Data-sharing procedure and agreements | Some external-sharing arrangements require review | Medium | Review arrangements and document purpose, legal basis and safeguards | IG Lead | 60 days | Open |
| Records management | Records management policy | Limited evidence of routine records-management reviews | Medium | Establish scheduled reviews for accuracy, retention, storage and disposal | Records Manager | 90 days | Open |
| SAR process | SAR procedure and tracking log | Procedure and response tracking are maintained | Low | Continue monitoring and conduct periodic quality checks | IG Team | Ongoing | In Progress |
| Supplier management | Supplier register and contracts | Privacy/security due diligence is inconsistent for some suppliers | High | Complete risk-based supplier privacy/security assessments | Procurement/IG | 60 days | Open — High Priority |
| Information Asset Register | Information Asset Register | Newer systems are not fully reflected in the register | Medium | Update the register and assign an information asset owner to each asset | Information Asset Owners | 60 days | Open |

3. Key Audit Observation

3.1 Privacy Notice.

The privacy notice provides a basic explanation of how LillyPut uses personal information but does not clearly describe every relevant processing activity.

Priority: Medium

Owner: DPO/IG Lead

Deadline: 45 days

Status: Open

The organisation should ensure its privacy information accurately reflects its current processing activities and explains purposes, lawful bases, data sharing, retention and individual rights.

3.2 DPIAs.

The absence of a central DPIA register is the most significant governance gap identified during this mini audit.

Priority: High

Owner: DPO/IG Lead

Deadline: 30 days

Status: Open — High Priority.

A central register should record:

  - Project/activity

  - DPIA screening decision

  - DPIA status

  - Identified risks

  - Mitigation measures

  - Owner

  - Approval date

  - Review date

3.3 Supplier Management

LillyPut relies on external providers for services such as care-management software, cloud storage, IT support and payroll.

The audit found that supplier privacy/security checks are not consistently documented.

Priority: High

Owner: Procurement/IG

Deadline: 60 days

Status: Open — High Priority

A risk-based supplier assessment should consider:

- Personal information processed

- Processing purpose

- Security controls

- Contractual requirements

- Data-breach arrangements

- Sub-processors

- Data locations and international transfers where applicable

- Retention and deletion arrangements

3.4 Staff Training

The fictional training report shows “82% completion”, leaving 18% outstanding.

Priority:  Medium

Owner: HR/Managers

Deadline: 30 days

Status: Open

Managers should follow up outstanding training and report completion to the appropriate governance forum.

4. Audit Action Tracker

| Ref | Action | Risk | Owner | Deadline | Status | Follow-up Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| AUD-01 | Create DPIA register and screening process | High | DPO/IG Lead | 30 days | Open | Approved DPIA register and screening form |
| AUD-02 | Complete supplier privacy/security assessments ¦ | High | Procurement/IG | 60 days | Open | Completed supplier assessments |
| AUD-03 | Complete outstanding staff training | Medium | HR/Managers | 30 days | Open | Updated training report |
| AUD-04 | Update privacy notice | Medium | DPO/IG Lead | 45 days | Open | Approved revised privacy notice |
| AUD-05 | Complete retention schedule | Medium | Records Manager | 60 days | Open | Updated retention schedule |
| AUD-06 | Review data-sharing arrangements | Medium | IG Lead | 60 days | Open | Reviewed agreements/register |
| AUD-07 | Update Information Asset Register | Medium | Information Asset Owners | 60 days | Open | Updated IAR with assigned owners |
| AUD-08 | Conduct breach-response exercise | Medium | IG/IT/Management | 60 days | Open | Exercise record and lessons learned |
| AUD-09 | Evidence records-management reviews | Medium | Records Manager | 90 days | Open | Review records and disposal evidence |
| AUD-10 | Continue access reviews | Low | IT/System Owners | Ongoing | In Progress | Access-review records |
| AUD-11 | Continue SAR monitoring | Low | IG Team | Ongoing | In Progress | SAR tracking and QA records |

5. Overall Audit Summary

The mini audit identified that LillyPut Healthcare Ltd has several important privacy controls in place, including a privacy notice, access reviews, staff training, breach procedures, SAR procedures and records-management arrangements.

However, improvement is required in several areas.

The “highest-priority findings” are:

1. “No central DPIA register”

2. “Inconsistent supplier privacy/security due diligence”

The audit action tracker assigns each finding an “owner, deadline, status and required evidence”, allowing management to monitor remediation through to closure.

A follow-up audit should verify whether corrective actions have been implemented effectively rather than relying solely on management confirmation.

Portfolio Skills Demonstrated

This project demonstrates:

- Privacy compliance auditing

- Evidence-based assessment

- Gap analysis

- Risk identification

- Risk rating

- Data protection governance

- DPIA management

- Supplier risk management

- Records management

- SAR processes

- Information asset management

- Audit recommendations

- Remediation tracking

- Action ownership and deadline management

- Audit follow-up and closure